## Sheet1
SR. NO. | PHASES | WEEK | DATE | DAY | DETAILS | DONE/ NOT DONE
1 | PHASE-1(MONTH-1) | WEEK-1 | 18.08.2025 | Monday | Our team members met together and discussed the project topic “PriHub – Support for Cognitive Disabilities”. Roles were divided among us (leader, documentation, survey, technical).
|  |  | 19.08.2025 | Tuesday | We carefully read through the DST project guidelines and our submitted proposal to make sure we understood what is expected.
|  |  | 20.08.2025 | Wednesday | We listed the people who will be important for this project, such as doctors, therapists, NGOs, teachers, and students with special needs.
|  |  | 21.08.2025 | Thursday | The team discussed the common issues faced by people with cognitive disabilities while using normal websites (like small text, too much content, or lack of voice support).
|  |  | 22.08.2025 | Friday | Together we drafted the first set of project goals, like making a user-friendly, accessible, and supportive platform.
|  |  | 23.08.2025 | Saturday | We met our mentor, presented these initial goals, and got suggestions to refine them further.
|  |  | 24.08.2025 | Sunday
|  | WEEK-2 | 25.08.2025 | Monday | We prepared survey forms and interview questions to collect feedback from caregivers, students, and teachers.
|  |  | 26.08.2025 | Tuesday | The team conducted short interviews with local doctors and therapists to understand their needs for such a platform.
|  |  | 27.08.2025 | Wednesday | We spoke with students and peers to collect opinions on what features they think could help.
|  |  | 28.08.2025 | Thursday | Each member researched existing accessibility tools like text-to-speech, high-contrast themes, and dyslexia-friendly fonts.
|  |  | 29.08.2025 | Friday | We looked into some existing applications and websites to see their strengths and weaknesses.
|  |  | 30.08.2025 | Saturday | As a team, we combined all the collected feedback and noted down the most important points.
|  |  | 31.08.2025 | Sunday
|  | WEEK-3 | 01.09.2025 | Monday | We divided the requirements into two groups: – Functional (features like login, chatbot, reminders, support tools), – Non-functional (things like security, easy usage, and scalability).
|  |  | 02.09.2025 | Tuesday | Created user personas (example: a student with dyslexia, a therapist providing resources, a caregiver managing reminders).
|  |  | 03.09.2025 | Wednesday | Wrote simple use-case stories to show how each type of user would interact with the platform.
|  |  | 04.09.2025 | Thursday | Discussed which technologies (React for frontend, Node.js + Firebase for backend) are suitable for our project.
|  |  | 05.09.2025 | Friday | Marked which requirements are essential (must-haves like accessibility features) and which can be optional for later.
|  |  | 06.09.2025 | Saturday | Shared these results with our mentor and refined the list further after feedback.
|  |  | 07.09.2025 | Sunday
|  | WEEK-4 | 08.09.205 | Monday | Started writing the Software Requirement Specification (SRS) document in a simple and clear format.
|  |  | 09.09.2025 | Tuesday | Added detailed points about accessibility standards like WCAG guidelines, ARIA labels, and special font/contrast settings.
|  |  | 10.09.2025 | Wednesday | Prepared a “requirement traceability matrix” to keep track of each requirement and its related feature.
|  |  | 11.09.2025 | Thursday | Team members reviewed the SRS internally to check for missing points or unclear sections.
|  |  | 12.09.2025 | Friday | Shared the draft with our mentor, who suggested some corrections and improvements.
|  |  | 13.09.2025 | Saturday | Made the corrections and finalized the requirement document. This marked the completion of Phase 1.
|  |  | 14.09.2025 | Sunday
2 | PHASE-2 (MONTH -2) | WEEK - 5 | 15.09.2025 | Monday | We started by deciding what we really want to know from the market study – who will use PriHub, what problems they face, and how current solutions help or fail.
|  |  | 16.09.2025 | Tuesday | We read about international accessibility standards like WCAG and ARIA to understand what features are considered “must-have” for disabled users.
|  |  | 17.09.2025 | Wednesday | We explored global platforms (like accessibility apps used abroad) to see what features they offer.
|  |  | 18.09.2025 | Thursday | We searched for Indian platforms or NGOs working in this field and noted what kind of digital tools they provide.
|  |  | 19.09.2025 | Friday | We compared the two and listed the gaps – for example, most apps don’t have simple navigation or a built-in assistant.
|  |  | 20.09.2025 | Saturday | As a team, we drafted the first version of our survey questions to ask real users and caregivers.
|  |  | 21.09.2025 | Sunday
|  | WEEK - 6 | 22.09.2025 | Monday | We simplified the survey questions into easy language so that anyone could answer without confusion.
|  |  | 23.09.2025 | Tuesday | Pelheiba created a Google Form for the survey and added our finalized questions.
|  |  | 24.09.2025 | Wednesday | We tested the form with 2–3 known people (friends/relatives) to check if it was easy to understand.
|  |  | 25.09.2025 | Thursday | Based on their suggestions, we made small corrections (like adding multiple-choice options instead of open-ended questions).
|  |  | 26.09.2025 | Friday | We started sharing the survey form in WhatsApp groups and through social media.
|  |  | 27.09.2025 | Saturday | We also sent the survey to some NGOs and people who support cognitive disability patients, asking them to circulate it further.
|  |  | 28.09.2025 | Sunday
|  | Week - 7 | 29.09.2025 | Monday | We began receiving responses and collected data from the first 30 participants.
|  |  | 30.09.2025 | Tuesday | We divided the responses into groups: students, parents, NGOs, and doctors.
|  |  | 01.10.2025 | Wednesday | We studied the answers related to “biggest difficulties” (like reading long text or using complicated menus).
|  |  | 02.10.2025 | Thursday | We studied the answers related to “what features they want” (like text-to-speech, reminders, or simple design).
|  |  | 03.10.2025 | Friday | We compared our findings with the features already available in existing apps and noted the gaps.
|  |  | 04.10.2025 | Saturday | We discussed what will make PriHub unique – for example, our AI chatbot + easy support tools in one platform.
|  |  | 05.10.2025 | Sunday
|  | WEEK - 8 | 06.10.2025 | Monday | We turned our survey results into simple charts and graphs for better understanding.
|  |  | 07.10.2025 | Tuesday | Pranjal and Vishakha worked on estimating the costs and revenue models to see if the project can be sustainable.
|  |  | 08.10.2025 | Wednesday | We compared free open-source tools with expensive commercial software to decide what we can use.
|  |  | 09.10.2025 | Thursday | We prepared the first draft of our Market Analysis Report, which included findings, graphs, and comparisons.
|  |  | 10.10.2025 | Friday | We presented this draft to our mentor, received his suggestions, and noted the changes.
|  |  | 11.10.2025 | Saturday | We finalized the Phase 2 report with survey analysis, feedback summaries, and a clear idea of what PriHub should include.
|  |  | 12.10.2025 | Sunday
3 | PHASE-3 (MONTH - 3) | WEEK - 9 | 13.10.2025 | Monday | We began by studying existing platforms for people with disabilities. Most of them lacked proper accessibility and were difficult to use.
|  |  | 14.10.2025 | Tuesday | We focused on problems faced by users with cognitive and visual impairments. They struggle with complicated designs, missing text-to-speech support, and confusing navigation.
|  |  | 15.10.2025 | Wednesday | We listed common issues such as lack of community features, fewer support options, and low inclusivity.
|  |  | 16.10.2025 | Thursday | We went through case studies and user reviews to understand where existing accessibility tools fail.
|  |  | 17.10.2025 | Friday | We compared traditional websites and found that many don’t include features like screen reader support, simplified text, or voice-based navigation.
|  |  | 18.10.2025 | Saturday | We shared our initial findings with our mentor for review and feedback.
|  |  | 19.10.2025 | Sunday
|  | WEEK - 10 | 20.10.2025 | Monday | We organized the problems into groups – Accessibility, Communication, Engagement, and Community Support.
|  |  | 21.10.2025 | Tuesday | We studied accessibility issues in detail – missing high-contrast modes, no dyslexia-friendly fonts, and no ARIA support for screen readers.
|  |  | 22.10.2025 | Wednesday | We discussed communication gaps such as no chatbot assistance, lack of tutorials, and unclear navigation paths.
|  |  | 23.10.2025 | Thursday | We identified engagement issues like users leaving early, lack of reminders, and no personalization.
|  |  | 24.10.2025 | Friday | We studied the lack of community support – no peer forums, no group discussions, and no option for therapist booking.
|  |  | 25.10.2025 | Saturday | We shared the categorized problems with our mentor to check if we covered everything correctly.
|  |  | 26.10.2025 | Sunday
|  | WEEK - 11 | 27.10.2025 | Monday | We focused on PriHub’s accessibility-first design, which includes features like screen reader compatibility, high-contrast mode, and dyslexia-friendly text.
|  |  | 28.10.2025 | Tuesday | We studied the AI-powered chatbot, which gives real-time guidance, navigation support, and answers user queries.
|  |  | 29.10.2025 | Wednesday | We explored PriHub’s productivity tools such as reminders, notes, and focus mode that help users manage daily tasks.
|  |  | 30.10.2025 | Thursday | We highlighted PriHub’s community features like peer forums and therapist booking, which provide emotional and professional support.
|  |  | 31.10.2025 | Friday | We studied PriHub’s scalable and low-cost technology (Node.js + Firebase), which makes it affordable for NGOs, schools, and healthcare providers.
|  |  | 01.11.2025 | Saturday | We presented these features to our mentor and refined them based on his suggestions.
|  |  | 02.11.2025 | Sunday
|  | WEEK - 12 | 03.11.2025 | Monday | We prepared a comparison table showing existing problems on one side and PriHub’s solutions on the other.
|  |  | 04.11.2025 | Tuesday | We rewrote the uniqueness section in simple language, focusing on empathy-driven and inclusion-first design.
|  |  | 05.11.2025 | Wednesday | We created diagrams and flowcharts to visually explain the problems and our solutions.
|  |  | 06.11.2025 | Thursday | We improved our documentation after discussing it with our mentor.
|  |  | 07.11.2025 | Friday | We finalized the Stage 3 report and ensured that everything was clear and well-structured.
|  |  | 08.11.2025 | Saturday | We presented our Stage 3 work to the mentor, got his approval, and marked this stage as completed.
|  |  | 09.11.2025 | Sunday
4 | PHASE-4 (MONTH - 4) | WEEK - 13 | 10.11.2025 | Monday | Create rough sketches (paper/wireframes) of home page, login, chatbot, support tools.
|  |  | 11.11.2025 | Tuesday | Design navigation flow (Home → Login → Dashboard → Resources → Chatbot).
|  |  | 12.11.2025 | Wednesday | Decide accessibility features (high-contrast, text resize, dyslexia fonts, screen reader support).
|  |  | 13.11.2025 | Thursday | Make low-fidelity prototypes in Canva.
|  |  | 14.11.2025 | Friday | Convert key wireframes into digital mockups with responsive layout.
|  |  | 15.11.2025 | Saturday | Team discussion + mentor review on UI mockups.
|  |  | 16.11.2025 | Sunday
|  | WEEK - 14 | 17.11.2025 | Monday | Finalize color themes & typography (accessible fonts, contrast ratios).
|  |  | 18.11.2025 | Tuesday | Create UI kit (buttons, forms, alerts, chatbot window, reminders panel).
|  |  | 19.11.2025 | Wednesday | Design Login & Signup Modals (with Firebase integration in mind).
|  |  | 20.11.2025 | Thursday | Design Chatbot UI (floating button, chat window, voice-to-text option).
|  |  | 21.11.2025 | Friday | Create Resource Directory Page (list view, categories, search).
|  |  | 22.11.2025 | Saturday | Finalize all frontend design mockups → Save design system.
|  |  | 23.11.2025 | Sunday
|  | WEEK - 15 | 24.11.2025 | Monday | Define system architecture (Client → API → Firebase DB → OpenAI API).
|  |  | 25.11.2025 | Tuesday | Design Entity-Relationship Diagram (ERD) (Users, Resources, Chatbot logs, Reminders).
|  |  | 26.11.2025 | Wednesday | Plan Firebase Database schema (Collections: Users, Resources, Notes, Chat logs).
|  |  | 27.11.2025 | Thursday | Design API endpoints (Login, Signup, Chat, Save Notes, Fetch Resources).
|  |  | 28.11.2025 | Friday | Plan Authentication flow (Email/Password, Google/GitHub/Facebook).
|  |  | 29.11.2025 | Saturday | Define Security Rules (Firebase rules for user data, encrypted storage).
|  |  | 30.11.2025 | Sunday
|  | WEEK - 16 | 01.12.2025 | Monday | Map Frontend components → Backend APIs (e.g., chatbot UI → /api/chat).
|  |  | 02.12.2025 | Tuesday | Create Sequence Diagrams (Login process, Chat interaction, Reminder setup).
|  |  | 03.12.2025 | Wednesday | Design System Flowchart (User journey from login → cognitive tools → chatbot).
|  |  | 04.12.2025 | Thursday | Define Error Handling & Notifications design (e.g., invalid login, chatbot timeout).
|  |  | 05.12.2025 | Friday | Conduct team review session: Validate both frontend and backend design documents.
|  |  | 06.12.2025 | Saturday | Mentor approval of final design → Stage 4 completed.
|  |  | 07.12.2025 | Sunday
5 | PHASE-5 (MONTH - 5) | WEEK - 17 | 08.12.2025 | Monday | Set up everything we need for coding, like software tools (VS Code, Node.js), GitHub for saving code.
|  |  | 09.12.2025 | Tuesday | Create the base project folder and connect Firebase to the project. This gives us the foundation.
|  |  | 10.12.2025 | Wednesday | Create the project folders and basic files (index.html, main.js, server.js, etc.).
|  |  | 11.12.2025 | Thursday | Build the home page layout with navigation bar, header, and footer using React.
|  |  | 12.12.2025 | Friday | Add placeholders for pages (Home, About, Resources, Support, Contact) & Write simple CSS to make the layout responsive on laptops and mobiles.
|  |  | 13.12.2025 | Saturday | Add some accessibility basics like a high-contrast mode and larger text options for easier reading.
|  |  | 14.12.2025 | Sunday
|  | WEEK - 18 | 15.12.2025 | Monday | Review the basic UI with mentor and teammates, making changes if needed.
|  |  | 16.12.2025 | Tuesday | Connect Firebase Authentication to our app.
|  |  | 17.12.2025 | Wednesday | Build a signup form where users can register with their email and password.
|  |  | 18.12.2025 | Thursday | Build a login form so registered users can sign in.
|  |  | 19.12.2025 | Friday | Add social login options (Google, GitHub, Facebook).
|  |  | 20.12.2025 | Saturday | Test all login methods and fix small bugs.
|  |  | 21.12.2025 | Sunday
|  | WEEK - 19 | 22.12.2025 | Monday | Create a user dashboard page that shows user details after login.
|  |  | 23.12.2025 | Tuesday | Meet with mentor to review the authentication system and get feedback.
|  |  | 24.12.2025 | Wednesday | Setup Node.js server using Express. This will handle requests from the frontend.
|  |  | 25.12.2025 | Thursday | Create backend routes like /api/chat and /api/reminder.
|  |  | 26.12.2025 | Friday | Connect Firebase Realtime Database to store user data (notes, reminders).
|  |  | 27.12.2025 | Saturday | Allow the frontend to save and retrieve reminders from the database.
|  |  | 28.12.2025 | Sunday
|  | WEEK - 20 | 29.12.2025 | Monday | Secure the backend so only logged-in users can access their data.
|  |  | 30.12.2025 | Tuesday | Review backend progress with mentor and ensure database is working fine.
|  |  | 31.12.2025 | Wednesday | Connect OpenAI API with backend to make chatbot replies work.
|  |  | 01.01.2026 | Thursday | Build chatbot UI on the frontend with a floating chat icon and chat box.
|  |  | 02.01.2026 | Friday | Add cognitive support tools like: Text-to-speech (reads content aloud), Simplified text mode (easy reading), Reminder & Notes panel, High contrast mode
|  |  | 03.01.2026 | Saturday | Do a full test of the system – login, chatbot, reminders, accessibility tools – and prepare for Stage 6 (Testing).
|  |  | 04.01.2026 | Sunday
6 | PHASE-6 (MONTH - 6) | WEEK - 21 | 05.01.2026 | Monday | Set up testing tools (Jest, Mocha, or Firebase Test Lab) and prepare test cases.
|  |  | 06.01.2026 | Tuesday | Install necessary dependencies for testing and create sample data for testing.
|  |  | 07.01.2026 | Wednesday | Write unit test scripts for small modules (frontend UI components).
|  |  | 08.01.2026 | Thursday | Write unit test scripts for backend modules (API endpoints, Firebase authentication).
|  |  | 09.01.2026 | Friday | Connect frontend React components with backend Node.js API.
|  |  | 10.01.2026 | Saturday | Test login and signup integration with Firebase.
|  |  | 11.01.2026 | Sunday
|  | WEEK - 22 | 12.01.2026 | Monday | Integrate AI chatbot with frontend and backend, check real-time responses.
|  |  | 13.01.2026 | Tuesday | Verify communication between cognitive tools (text-to-speech, reminders) and database.
|  |  | 14.01.2026 | Wednesday | Test accessibility features – screen reader compatibility, high-contrast mode, keyboard navigation.
|  |  | 15.01.2026 | Thursday | Test text-to-speech and simplified text functionalities across different pages.
|  |  | 16.01.2026 | Friday | Test chatbot responses with multiple queries and ensure accuracy.
|  |  | 17.01.2026 | Saturday | Check cross-browser functionality (Chrome, Edge, Firefox, mobile browsers).
|  |  | 18.01.2026 | Sunday
|  | WEEK - 23 | 19.01.2026 | Monday | Conduct load testing (multiple users logging in simultaneously).
|  |  | 20.01.2026 | Tuesday | Fix identified bugs in authentication and chatbot responses.
|  |  | 21.01.2026 | Wednesday | Optimize UI for faster loading and mobile responsiveness.
|  |  | 22.01.2026 | Thursday | Conduct security testing – check unauthorized access and session handling.
|  |  | 23.01.2026 | Friday | Conduct testing sessions with classmates/volunteers simulating users with cognitive challenges.
|  |  | 24.01.2026 | Saturday | Collect user feedback on accessibility and ease of navigation.
|  |  | 25.01.2026 | Sunday
|  | WEEK - 24 | 26.01.2026 | Monday | Refine chatbot responses and improve reminder/notes functionality.
|  |  | 27.01.2026 | Tuesday | Fix bugs found during user testing and update documentation.
|  |  | 28.01.2026 | Wednesday | Re-test all modules after fixes (regression testing).
|  |  | 29.01.2026 | Thursday | Validate database consistency and check for data loss during operations.
|  |  | 30.01.2026 | Friday | Conduct final system testing (end-to-end: login → chatbot → notes → logout).
|  |  | 31.01.2026 | Saturday | Mentor review, sign-off, and prepare summary report for Phase 6.
|  |  | 01.02.2026 | Sunday
7 | PHASE-7 (MONTH - 7) | WEEK - 25 | 02.02.2026 | Monday | The team sat together to discuss all the resources we used during the project – software, hardware, domain, internet, and other small materials. We listed them one by one to make sure nothing was missed.
|  |  | 03.02.2026 | Tuesday | Each member was given the task to search for price details. We looked up the cost of software licenses, server charges, hosting plans, and developer tools that were used.
|  |  | 04.02.2026 | Wednesday | We worked on estimating hardware costs. Since most of us used personal laptops and mobile devices, we decided to add approximate depreciation and utility costs for these.
|  |  | 05.02.2026 | Thursday | The focus was on development tools. We checked how much we spent (or would have spent) on React.js libraries, Firebase, Node.js packages, and deployment tools.
|  |  | 06.02.2026 | Friday | We calculated expenses for documentation like printing, binding, and creating project presentations. These are small costs but necessary to include.
|  |  | 07.02.2026 | Saturday | Finally, we added consumable costs such as internet data, electricity usage, and stationery. By the end of this week, we had a rough list of every possible cost item.
|  |  | 08.02.2026 | Sunday
|  | WEEK - 26 | 09.02.2026 | Monday | Using the data collected, we prepared a first draft of the total budget sheet. This included both direct expenses (domain, printing) and indirect expenses (electricity, internet).
|  |  | 10.02.2026 | Tuesday | We compared the budget with the funding amount sanctioned by the Department of Science & Technology. This helped us check if we stayed within the given limit.
|  |  | 11.02.2026 | Wednesday | Each cost item was justified. For example, we explained why we needed a domain purchase, why Firebase authentication was chosen, and why printing and binding were necessary.
|  |  | 12.02.2026 | Thursday | We showed the draft to our mentor for feedback. He suggested that we make the costs more realistic and ensure no duplication of entries.
|  |  | 13.02.2026 | Friday | After corrections, we finalized the Cost Estimation Sheet with clear categories – Software, Hardware, Documentation, Consumables, and Miscellaneous.
|  |  | 14.02.2026 | Saturday | We prepared a short summary of the total budget in both table and paragraph form, so it could be directly inserted into the final report.
|  |  | 15.02.2026 | Sunday
|  | WEEK - 27 | 14.02.2026 | Monday | The team created an outline of the report. It was divided into sections: Abstract, Introduction, Problem Statement, Methodology, Implementation, Cost Estimation, Testing, Conclusion, and Future Scope.
|  |  | 15.02.2026 | Tuesday | We wrote the Abstract and Objectives in simple and clear language. The goal was to summarize the project in less than a page so that readers quickly understand it.
|  |  | 16.02.2026 | Wednesday | The Methodology section was documented. This explained the technologies we used – React.js for frontend, Node.js for backend, Firebase for authentication and database, and OpenAI for chatbot integration.
|  |  | 17.02.2026 | Thursday | We worked on the Cost Estimation section. This included tables for each cost item and graphs showing the distribution of the total budget across software, hardware, and documentation.
|  |  | 18.02.2026 | Friday | The Implementation and Testing Results were added. We wrote about how each module was built, tested, and improved.
|  |  | 19.02.2026 | Saturday | Finally, we drafted the Conclusion and Future Scope. This part explained how the project could be improved further by adding more accessibility features and community tools.
|  |  | 20.02.2026 | Sunday
|  | WEEK - 28 | 21.02.2026 | Monday | The entire report draft was proofread. We corrected spelling, grammar, and formatting mistakes. This step made the report more professional.
|  |  | 22.02.2026 | Tuesday | Formatting work was done – consistent font styles, proper headings, numbered tables and figures, and page numbering.
|  |  | 23.02.2026 | Wednesday | Screenshots, diagrams, and flowcharts were inserted into the report. These visuals made the report easier to understand.
|  |  | 24.02.2026 | Thursday | We prepared the Bibliography and Appendices. The bibliography listed all references, while the appendices included survey forms, screenshots, and extra documents.
|  |  | 25.02.2026 | Friday | The mentor reviewed the report. He suggested a few small changes in the conclusion and formatting. We updated those immediately.
|  |  | 26.02.2026 | Saturday | The final version was printed, spiral bound, and submitted officially. A soft copy was also prepared for digital submission.
|  |  | 27.02.2026 | Sunday